## Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 - Coordinator Dashboard
Task 1 - creating required fields (ex: name, min cgpa etc) |  | Yes | Medium | Complete |  | Yes
Task 2 - Validation of fields (ex: cgpa shouldn't exceed 10) |  | Yes | Medium | Complete |  | Yes
Task 3 - Reflect to the database at the backend |  | Yes | Medium | Complete |  | Yes
Sprint 2 - Student login and registration and apply drives
Apply (student flow) |  | Yes | High | Not complete |  | No
Connect the database at the backend |  | Yes | High | Completed |  | Yes
Sprint 3 - Faculty dashboard & testing
Task 7 |  | No | Low | In Progress | 8 | No
Task 8 |  | No | Medium | In Progress | 8 | No
Task 9 |  | Yes | Medium | In Progress | 16 | No

## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Student Placement Coordinator adding and deleting placment drives | As a student placement co-ordinator I want to post company drives | Yes | High | Complete |  | Yes
Task 1-creating required fields(ex:name,min cgpa etc) | Yes | Yes | Medium | Complete |  | Yes
Task 2-Validation of fields(ex: cgpa shouldn't extend 10) | Yes | Yes | Medium | Complete |  | Yes
Task 3-Reflect to the database at the backend | Yes | Yes | Medium | Complete |  | Yes
Sprint2 - Student login and registration and apply drivees | As a student I want to login so that I apply for drives | Yes | High | Complete |  | Yes
apply | Yes | Yes | high | Not complete |  | No
Connect the database at the backend | yes | yes | high | completed |  | Yes
Sprint 3 | No | No | Medium | In Progress |  | No
Task 7 | No | No | Low | In Progress | 8 | No
Task 8 | No | no | Medium | In Progress | 8 | No
Task 9 | Yes | No | Medium | In Progress | 16 | No
Sprint 4 | No | No | Medium | In Progress |  | Yes
Task 10 | Yes | No | Low | In Progress | 32 | No
Task 11 | Yes | no | Low | Complete | 32 | Yes
Task 12 | Yes | no | Medium | Complete | 0 | Yes
Sprint 5 | No | No | Low | Not Started |  | No
Task 13 | No | No | Low | Not Started | 48 | No
Task 14 | No | No | Low | Not Started | 8 | No
Task 15 | No | No | Low | Not Started | 8 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started

## Sprint 1 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Coordinator Authentication | Implement login page and integrate with API | Frontend | Coordinator can log in and see dashboard | 3 | Not Started
Coordinator Authentication | Ensure backend login route is called and errors handled | Backend | 401 on invalid creds | 2 | Not Started
Drive Management | Implement drive create form with file upload | Frontend | Drive created and appears in list | 5 | Not Started
Drive Management | Implement POST /api/drives handling file and data | Backend | Drive record contains jdUrl | 5 | Not Started
Drive Management | Implement drive edit/delete UI and endpoints | Both | Edit updates fields; delete removes drive | 5 | Not Started
Material Hub | Implement material upload and list UI | Frontend | Uploaded material shows with download link | 3 | Not Started
Material Hub | Implement POST/DELETE /api/materials | Backend | Material record contains fileUrl; delete removes record | 3 | Not Started
Student Status Management | UI for placed/blacklist toggles | Frontend | State updates in UI and persists | 2 | Not Started
Student Status Management | Implement PATCH /api/students/:id/status | Backend | Student flags updated in DB | 2 | Not Started
Validation Tests | Write API checks for required fields and enum degree | Backend | Invalid inputs return 400 | 3 | Not Started

## Sprint 2 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Student Registration | Create registration form with resume upload | Frontend | Student can register and resume saved | 5 | Not Started
Student Registration | Implement POST /api/students/register | Backend | 409 on duplicate email/regno; password hashed | 5 | Not Started
Student Login & Profile | Implement student login and profile edit UI | Frontend | Student can login and update profile | 3 | Not Started
Student Login & Profile | Implement PATCH /api/students/:id | Backend | Profile updates persist and maintain uniqueness | 3 | Not Started
Drive Application | Implement apply button and flow (frontend) | Frontend | Eligible students can apply; UI handles errors | 3 | Not Started
Drive Application | Implement POST /api/drives/:id/apply | Backend | Controller enforces eligibility and appends application | 5 | Not Started
Validation Tests | Add tests for registration uniqueness and CGPA checks | Backend | Tests assert correct status codes and messages | 3 | Not Started

## Sprint 3 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Faculty Login | Create faculty login UI and integrate with API | Frontend | Faculty can login successfully | 2 | Not Started
Faculty Login | Ensure backend /api/auth/faculty/login validity | Backend | 401 on invalid creds | 2 | Not Started
E2E Validation Testing | Define test cases for all validations (list) | QA | Tests covering registration, login, drive create, apply flows | 5 | Not Started
E2E Validation Testing | Execute tests and record pass/fail | QA | Test report produced with defects listed | 5 | Not Started
Regression & Acceptance | Run manual acceptance scenarios and fix defects | Both | Bugs fixed and acceptance sign-off | 3 | Not Started