## Sheet1
Test Plan
Project Name | SCIS School Placement portal |  |  |  | Browser:
Test Case ID | 101 |  |  |  | Version:
Written By: | Meghasyam |  |  |  | Description:
Tested By: | Sujeeth |  |  |  | Tested On:
Test case for sprint-1
Test # | Date | Field | Action | Input | Expected Results | Actual Results | Pass?
1 | 2026-03-12 | Company Name | isAlphanumeric | Amazon | Valid | Valid | Pass
2 | 2026-03-12 | CGPA | isNumeric | 8.6 | Valid | Valid | Pass
3 | 2026-03-14 | CGPA | isNumeric | 11 | Invalid | Invalid | Pass
4 | 2026-03-14 | Branch | checkBox | not selected any check box | Invalid | Invalid | Pass
Test Case for Sprint- 2
1 | 2026-03-15 | Registration Number | isAlphanumeric(unique) | 25mcmt20 | valid | valid | Pass
2 | 2026-03-15 | Password | isAlphanumeric with special character | Syam@2110 | valid | valid | Pass
3 | 2026-03-16 | Apply | Is Set CGPA == student cgpa | apply | valid | valid | Pass

## Sheet2
FALSE
TRUE
FALSE
TRUE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Sprint 1 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Coordinator Authentication | Implement login page and integrate with API | Frontend | Coordinator can log in and see dashboard | 3 | Not Started
Coordinator Authentication | Ensure backend login route is called and errors handled | Backend | 401 on invalid creds | 2 | Not Started
Drive Management | Implement drive create form with file upload | Frontend | Drive created and appears in list | 5 | Not Started
Drive Management | Implement POST /api/drives handling file and data | Backend | Drive record contains jdUrl | 5 | Not Started
Drive Management | Implement drive edit/delete UI and endpoints | Both | Edit updates fields; delete removes drive | 5 | Not Started
Material Hub | Implement material upload and list UI | Frontend | Uploaded material shows with download link | 3 | Not Started
Material Hub | Implement POST/DELETE /api/materials | Backend | Material record contains fileUrl; delete removes record | 3 | Not Started
Student Status Management | UI for placed/blacklist toggles | Frontend | State updates in UI and persists | 2 | Not Started
Student Status Management | Implement PATCH /api/students/:id/status | Backend | Student flags updated in DB | 2 | Not Started
Validation Tests | Write API checks for required fields and enum degree | Backend | Invalid inputs return 400 | 3 | Not Started

## Sprint 2 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Student Registration | Create registration form with resume upload | Frontend | Student can register and resume saved | 5 | Not Started
Student Registration | Implement POST /api/students/register | Backend | 409 on duplicate email/regno; password hashed | 5 | Not Started
Student Login & Profile | Implement student login and profile edit UI | Frontend | Student can login and update profile | 3 | Not Started
Student Login & Profile | Implement PATCH /api/students/:id | Backend | Profile updates persist and maintain uniqueness | 3 | Not Started
Drive Application | Implement apply button and flow (frontend) | Frontend | Eligible students can apply; UI handles errors | 3 | Not Started
Drive Application | Implement POST /api/drives/:id/apply | Backend | Controller enforces eligibility and appends application | 5 | Not Started
Validation Tests | Add tests for registration uniqueness and CGPA checks | Backend | Tests assert correct status codes and messages | 3 | Not Started

## Sprint 3 Backlog
Story | Task | Area | Acceptance Criteria | Estimate | Status
Faculty Login | Create faculty login UI and integrate with API | Frontend | Faculty can login successfully | 2 | Not Started
Faculty Login | Ensure backend /api/auth/faculty/login validity | Backend | 401 on invalid creds | 2 | Not Started
E2E Validation Testing | Define test cases for all validations (list) | QA | Tests covering registration, login, drive create, apply flows | 5 | Not Started
E2E Validation Testing | Execute tests and record pass/fail | QA | Test report produced with defects listed | 5 | Not Started
Regression & Acceptance | Run manual acceptance scenarios and fix defects | Both | Bugs fixed and acceptance sign-off | 3 | Not Started

## Test Plan
Test ID | Title | Description | Precondition | Steps | Expected Result | Priority | Sprint | Status
TP-01 | Student Registration - required fields | Verify registration fails when required fields are missing | None | Submit registration missing email or regno | 400 with message "Please fill all required fields." | High | Sprint 2 | Not Executed
TP-02 | Student Registration - duplicate email/regno | Verify registration returns 409 for duplicate email or regno | Existing student with same email/regno | Submit registration with duplicate email/regno | 409 with duplicate message | High | Sprint 2 | Not Executed
TP-03 | Student Login - invalid credentials | Verify login returns 401 for wrong password | Registered student | Attempt login with wrong password | 401 with Invalid login credentials | High | Sprint 2 | Not Executed
TP-04 | Drive Creation - degree enum | Verify drive creation rejects invalid degree | Coordinator authenticated | POST /api/drives with degree invalid | 400 with degree validation message | Medium | Sprint 1 | Not Executed
TP-05 | Apply For Drive - CGPA check | Verify application fails if student CGPA < minCgpa | Drive with minCgpa set | Student with lower cgpa applies | 400 with min CGPA message | High | Sprint 2 | Not Executed
TP-06 | Export Applicants - file downloadable | Verify export returns XLSX for drive | Drive with applications | GET /api/drives/{id}/applications/export | 200 and content-disposition with .xlsx | Medium | Sprint 1 | Not Executed